## Schedule
Win7 / MMS - MPSD Deployment Request - OpsEng
step | task | owner | start date | end date | duration | actual duration | issues | notes
1 | Kick off and planning | OpsPM | 2011-04-01 | 2011-04-05 | 2 | 2
2 | provide info on new apps/drivers since last image | DMSAM | 2011-04-05 | 2011-04-07 | 2 | 2
3 | requirements spec & approval from customer | OpsPM | 2011-04-07 | 2011-04-15 | 5 | 6
4 | review & approve requirements spec | OpsDev | 2011-04-15 | 2011-04-19 | 2 | 2
5 | create image & task sequence | OpsDev | 2011-04-19 | 2011-04-26 | 5 | 5
6 | Update OEM Driver Packages | Ops Dev | 2011-04-19 | 2011-04-26 | NA
7 | internal test | DMSAM | 2011-04-26 | 2011-05-03 | 5 | 5
8 | move to \UAT | OpsDev | 2011-05-03 | 2011-05-05 | 2 | 2
9 | Customer UAT and sign off of TS | OpsPM | 2011-05-05 | 2011-05-06 | 1 | 1
10 | build SAM DVD & OEM media | OpsDev | 2011-05-06 | 2011-05-09 | 1 | 1
11 | replicate ISO and OEM files to UAT | OpsDev | 2011-05-09 | 2011-05-10 | 1 | 1
12 | IM pre-UAT x 2 | DMSInc | 2011-05-10 | 2011-05-13 | 3 | 3
13 | IM doc updates | DMSInc | 2011-05-13 | 2011-05-27 | 10 | 10
14 | Customer UAT | OpsPM | 2011-05-13 | 2011-05-20 | 5 | 5
15 | move to \production (DVD and TS) | OpsDev | 2011-05-20 | 2011-05-25 | 3 | 3
16 | DVD\ROQ | DMSAM | 2011-05-25 | 2011-06-08 | 10 | 10
17 | final sign off -release communication | OpsPM | 2011-06-08 | 2011-06-09 | 1 | 1
Change Due Date
New Schedule
Run Report
Actual Duration

## templates
MSIT - MPSD Operations SCRUM - User Story
Win7 / MSIT - MPSD Deployment Request - OpsEng
step | task | owner | start date | end date | duration (in days) | actual duration | issues | notes
1 | image schedule communicated & attached to user story | OpsPM |  |  | NA
2 | OSD requirements & Image spec communicated & attached | MSIT rep |  |  | 1
3 | open MPSD Deployment Request - with task sequence & replication checklists - attach req/spec | OpsPM |  |  | NA
4 | requirements & spec reviewed and approved | OpsDev |  |  | 1
5 | create TS | OpsDev |  |  | 3
6 | provide title & DOG location - hand off to OpsPM to coordinate internal testing | OpsDev |  |  | NA
7 | create task, link to story & communicate hand off to internal test | OpsPM |  |  | NA
8 | DMSAM test | DMSAM |  |  | 2
9 | QC test | MSIT test |  |  | 5
10 | pkg replication - move to production MSF\CAS | OpsDev |  |  | 3
11 | TS replication | OpsDev |  |  | 1
12 | complete boot image replication prep task list | OpsDev |  |  | 1
13 | coordinate replication & communicates to stakeholders when complete | MSIT rep |  |  | 10
14 | final sign off -release communication | OpsPM |  |  | 1
Win7 / MMS - MPSD Deployment Request - OpsEng
step | task | owner | start date | end date | duration | actual duration | issues | notes
1 | Kick off and planning | OpsPM |  |  | 2
2 | provide info on new apps/drivers since last image | DMSAM |  |  | 2
3 | requirements spec & approval from customer | OpsPM |  |  | 5
4 | review & approve requirements spec | OpsDev |  |  | 2
5 | create image & task sequence | OpsDev |  |  | 5
6 | Update OEM Driver Packages | Ops Dev |  |  | NA
7 | internal test | DMSAM |  |  | 5
8 | move to \UAT | OpsDev |  |  | 2
9 | Customer UAT and sign off of TS | OpsPM |  |  | 1
10 | build SAM DVD & OEM media | OpsDev |  |  | 1
11 | replicate ISO and OEM files to UAT | OpsDev |  |  | 1
12 | IM pre-UAT x 2 | DMSInc |  |  | 3
13 | IM doc updates | DMSInc |  |  | 10
14 | Customer UAT | OpsPM |  |  | 5
15 | move to \production (DVD and TS) | OpsDev |  |  | 3
16 | DVD\ROQ | DMSAM |  |  | 10
17 | final sign off -release communication | OpsPM |  |  | 1
XP / MMS - MPSD Deployment Request - OpsEng
step | task | owner | start date | end date | duration | actual duration | issues | notes
1 | Kick off and planning | OpsPM |  |  | 2
2 | provide info on new apps/drivers since last image | DMSAM |  |  | 2
3 | requirements spec & approval from customer | OpsPM |  |  | 5
4 | review & approve requirements spec | OpsDev |  |  | 2
5 | create image | OpsDev |  |  | 5
6 | internal test | DMSAM |  |  | 5
7 | move to \UAT | OpsDev |  |  | 1
8 | IM pre-UAT | DMSInc |  |  | 3
9 | IM doc updates | DMSInc |  |  | 10
10 | Customer UAT | OpsPM |  |  | 5
11 | move to \production | OpsDev |  |  | 5
12 | DVD\ROQ | DMSAM |  |  | 10
13 | final sign off -release communication | OpsPM |  |  | 1
Email | steps finished early: 3% steps finished late: 8% projects finished late: 57% projects finished early: 14%